|  |  |
| --- | --- |
| **Month** | **Action** |
| June/July(delivery year -2) | Initial discussions of ideas within the College, and with relevant professional services departments/committees |
| September/October(delivery year -2) | Consideration and approval within the College (Board of Studies & College Learning and Teaching Committee) |
| October/December(delivery year -2) | Deadline of consideration of New Programme Proposals by Programme Management Board.  Consideration by Collaborative Partnership Board, if required |
| January/March(delivery year -1) | Consideration of any new/amended regulations by the Academic Regulations and Cases Board,  due diligence reviews by the Collaborative Board (as necessary) |
| July(delivery year -1) | Last date for submission of programme proposals for consideration by the Programme Approval and Maintenance system Committee |
| July(delivery year -1) | Final date for Full Validation Events for new programme proposals |
| August(delivery -1) | Final date for fulfilment of conditions imposed by Programme Approval Committee |
| September(delivery -1) | Ratification by Senate |
| January(delivery year) | Swansea University Publications and UCAS deadline |
| ???? | Admissions UCAS/Prospectus???? |
| September/October | Launch of new programme |