|  |  |
| --- | --- |
| **Month** | **Action** |
| June/July  (delivery year -2) | Initial discussions of ideas within the College, and with relevant professional services departments/committees |
| September/October  (delivery year -2) | Consideration and approval within the College (Board of Studies & College Learning and Teaching Committee) |
| October/December  (delivery year -2) | Deadline of consideration of New Programme Proposals by Programme Management Board.  Consideration by Collaborative Partnership Board, if required |
| January/March  (delivery year -1) | Consideration of any new/amended regulations by the Academic Regulations and Cases Board,  due diligence reviews by the Collaborative Board (as necessary) |
| July  (delivery year -1) | Last date for submission of programme proposals for consideration by the Programme Approval and Maintenance system Committee |
| July  (delivery year -1) | Final date for Full Validation Events for new programme proposals |
| August  (delivery -1) | Final date for fulfilment of conditions imposed by Programme Approval Committee |
| September  (delivery -1) | Ratification by Senate |
| January  (delivery year) | Swansea University Publications and UCAS deadline |
| ???? | Admissions UCAS/Prospectus???? |
| September/October | Launch of new programme |